# Acme Facility Management

Kickoff Call — Meeting Recap

Prepared by: Jay Smith, 10x Velocity

Meeting date: April 14, 2026 [to confirm]

Attendees:

- Marcus — Director of Operations, Acme

- Diane — Accounting, Acme [name spelling to confirm]

- Facilities Coordinator, Acme [name to confirm]

- Jay Smith — 10x Velocity

# Action Items

| Action | Owner | Due |
| --- | --- | --- |
| Send capabilities one-pager to Acme | Jay (10x Velocity) | EOW — Fri, Apr 17 |
| Provide name of current CMMS and login for demo environment | Marcus (Acme) | Fri, Apr 24 |
| Schedule follow-up discovery session with Acme operations team | Jay (10x Velocity) | Week of Apr 20 |
| Draft rough scope document for internal review | Kirk (10x Velocity) | Prior to follow-up call |
| Review scope document before it is shared externally | Jay (10x Velocity) | Prior to follow-up call |
| Send calendar invite for follow-up call | Jay (10x Velocity) | Week of Apr 20 |

# Context & Discussion

## Objective

Acme is evaluating automation of its work order routing process. The objective of the kickoff was to understand current-state pain points, gather baseline operational data, and align on next steps toward a scoped engagement.

## Current State

- Work orders are managed through a combination of email and a shared Google Sheet.

- The shared sheet has not been consistently maintained; Acme confirmed it has not been synchronized since February.

- Work orders are being routed to technicians without consistent verification of required certifications.

- Example raised: HVAC tickets have been routed to general maintenance staff, occurring approximately two to three times per week.

## Compliance Note

Acme referenced an upcoming state inspection in Q3. This was flagged as a relevant timeline consideration and will be revisited in the follow-up discovery session.

## Budget

Marcus confirmed that budget has been approved for the current quarter. Specific figures were not discussed; 10x Velocity will align scope to Acme's budget parameters during the scoping phase.

# Open Questions

- Is Acme currently using HubSpot, GoHighLevel, or another CRM that would need to integrate with the work order solution?

- What is Acme's preferred approach to change management and technician training for a new routing workflow?

- Are there existing certification records per technician in a system we can draw from, or will those need to be captured?

# Items to Confirm

- Meeting date (April 14 or 15, 2026)

- Spelling of attendee name: Diane vs. Diana

- Name and title of the Acme Facilities Coordinator in attendance

- Name of Acme's current CMMS (Marcus to provide)

- Total technician headcount (initial estimate: 22–30, including part-time)

- Monthly work order volume (initial estimate: 400–600)

- Current CRM / system of record for customer and asset data

# Next Steps

10x Velocity will send the capabilities one-pager by end of week and coordinate a follow-up discovery session with Acme's operations team in the week of April 20. Kirk will prepare an initial scope document for internal review, with Jay reviewing prior to any external distribution. A calendar invite for the follow-up call will be sent separately.